## Project Plan
No.of days Until Today | No.of days | Target start date to Today | Project Name | Project Category | Ancestors | Project Manager | Phase/Milestone | Area | At Risk? | Schedule Health | Task Name | Status | % Complete | Start Date | End Date | Priority | Owner | On Hold? | Not Applicable? | Duration | Predecessors | Total Float | Critical ? | Baseline Start | Baseline Finish | Variance | Status Comment | Baseline Start Date | Baseline End Date | Comments | Assigned To | Start | Finish | Baseline Start2 | Baseline Finish2 | Variance2
[5 empty] | 0 |  |  |  |  | Green | Meridian HR Suite Rollout - Northwind Retail | In Progress
[5 empty] | 1 |  |  |  |  | Green | Contract Sign Off | Completed | 1 | 2026-03-04 | 2026-03-06 | [7 empty] | TRUE
[5 empty] | 1 |  |  |  |  | Green | Discovery & Requirements | Completed | 1 | 2026-03-09 | 2026-03-29 | [7 empty] | TRUE
[5 empty] | 1 |  |  |  |  | Green | Environment Setup | Completed | 1 | 2026-03-30 | 2026-04-08 | [5 empty] | 2
[5 empty] | 1 |  |  |  |  | Green | Core Configuration | Completed | 1 | 2026-04-09 | 2026-05-23 | [5 empty] | 3 |  | TRUE
[5 empty] | 1 |  |  |  |  | Green | Integration Build | In Progress | 0.8 | 2026-05-24 | 2026-07-07 | [5 empty] | 4 |  | TRUE |  |  |  | Tracking to plan, team is confident in the current timeline.
[5 empty] | 1 |  |  |  |  | Green | UAT Planning | In Progress | 0.5 | 2026-06-22 | 2026-07-12 | [5 empty] | 5
[5 empty] | 1 |  |  |  |  | Green | UAT Execution | Not Started | 0 | 2026-07-13 | 2026-08-01 | [5 empty] | 6
[5 empty] | 1 |  |  |  |  | Green | Go-Live Readiness | Not Started | 0 | 2026-08-02 | 2026-08-16 | [5 empty] | 7 |  | TRUE
[5 empty] | 1 |  |  |  |  | Green | Hypercare | Not Started | 0 | 2026-08-17 | 2026-08-31 | [5 empty] | 8

## Summary
Project Name | Meridian HR Suite Rollout - Northwind Retail
Project Manager | Ayesha Kulkarni
Project Start Date | 2026-03-04
Project End Date | 2026-08-31
Not Started | 3
In Progress | 2
Completed | 4
On Hold | 0
At Risk | Low
Project Stage | Build Phase
% Complete | 0.59
Schedule Health | Green
Today's Date | 2026-07-02
Project Status | In Progress