## Project Plan
No.of days Until Today | No.of days | Target start date to Today | Project Name | Project Category | Ancestors | Project Manager | Phase/Milestone | Area | At Risk? | Schedule Health | Task Name | Status | % Complete | Start Date | End Date | Priority | Owner | On Hold? | Not Applicable? | Duration | Predecessors | Total Float | Critical ? | Baseline Start | Baseline Finish | Variance | Status Comment | Baseline Start Date | Baseline End Date | Comments | Assigned To | Start | Finish | Baseline Start2 | Baseline Finish2 | Variance2
[5 empty] | 0 |  |  |  |  | Green | Orion ERP Migration - Falcon Manufacturing | In Progress
[5 empty] | 1 |  |  |  |  | Green | Contract Sign Off | Completed | 1 | 2026-02-02 | 2026-02-04 | [7 empty] | TRUE
[5 empty] | 1 |  |  |  |  | Yellow | Discovery & Requirements | Completed | 1 | 2026-02-05 | 2026-03-04 | [7 empty] | TRUE |  |  |  | Scope grew mid-phase, client kept adding requirements.
[5 empty] | 1 |  |  |  |  | Yellow | Data Migration Design | Completed | 1 | 2026-03-05 | 2026-03-29 | [5 empty] | 2 |  | TRUE |  |  |  | Design finalized late; client SME availability was a recurring issue.
[5 empty] | 1 |  |  |  |  | Red | Data Migration Build | In Progress | 0.35 | 2026-03-30 | 2026-06-02 | [5 empty] | 3 |  | TRUE |  |  |  | Significantly behind, two key resources reassigned off the project.
[5 empty] | 1 |  |  |  |  | Red | Integration Build | In Progress | 0.2 | 2026-05-03 | 2026-06-22 | [5 empty] | 3 |  | TRUE |  |  |  | Blocked waiting on client API credentials for three weeks.
[5 empty] | 1 |  |  |  |  | Red | Security Review | Not Started | 0 | 2026-06-12 | 2026-06-27 | [5 empty] | 5 |  | TRUE |  |  |  | Cannot start until integration build stabilizes; client escalating.
[5 empty] | 1 |  |  |  |  | Red | UAT Planning | Not Started | 0 | 2026-06-27 | 2026-07-17 | [5 empty] | 4 | [5 empty] | On hold pending scope re-baseline conversation with sponsor.
[5 empty] | 1 |  |  |  |  | Yellow | UAT Execution | Not Started | 0 | 2026-07-18 | 2026-08-06 | [5 empty] | 7
[5 empty] | 1 |  |  |  |  | Yellow | Go-Live Readiness | Not Started | 0 | 2026-08-07 | 2026-08-21 | [5 empty] | 8 |  | TRUE

## Summary
Project Name | Orion ERP Migration - Falcon Manufacturing
Project Manager | Marcus Webb
Project Start Date | 2026-02-02
Project End Date | 2026-08-21
Not Started | 4
In Progress | 2
Completed | 3
On Hold | 0
At Risk | High
Project Stage | Build Phase
% Complete | 0.39
Schedule Health | Red
Today's Date | 2026-07-02
Project Status | In Progress