## Slide 1
PROFESSIONAL SERVICES
Monthly Project Health Update
A portfolio-level view of schedule, milestone, and delivery risk across active engagements.
3 active projects reviewed
Snapshot as of 2026-07-09
Generated automatically by the Project Health Reporting Agent

## Slide 2
Portfolio Snapshot
Where the portfolio stands today, at a glance.
2
Red projects
0
Amber projects
1
Green projects
2 of 3 projects are Red
Schedule and milestone slippage are the most common drivers across the flagged projects -- not isolated, one-off issues.
Per-project detail
Orion ERP Migration - Falcon Manufacturing
Red
Marcus Webb
Zycus - UniSan S2P Implementation
Red
Rajat Bothra
Meridian HR Suite Rollout - Northwind Retail
Green
Ayesha Kulkarni
Source: weekly automated health scans across all active project plans.
As of 2026-07-09

## Slide 3
Trend Across Projects
Movement over the last three weekly scans -- direction matters as much as current color.
Orion ERP Migration - Falcon Manufacturing
Steady
06-18
06-25
07-02
07-09
Orion ERP Migration - Falcon Manufacturing is off track and needs immediate leadership intervention.
Zycus - UniSan S2P Implementation
Worsening
06-18
06-25
07-02
07-09
Zycus - UniSan S2P Implementation is off track and needs immediate leadership intervention.
Meridian HR Suite Rollout - Northwind Retail
Steady
06-18
06-25
07-02
07-09
Meridian HR Suite Rollout - Northwind Retail is healthy and on track.
Dots read left-to-right, oldest to most recent weekly scan.
As of 2026-07-09

## Slide 4
Emerging Risk: What's Actually Driving It
How many projects are flagged Amber/Red on each dimension -- the pattern, not just the count.
Chart: 
| Schedule | Milestones | Blockers | Sentiment
Projects flagged | 3 | 3 | 2 | 1
Read on the pattern
Schedule is the most common flag across the flagged projects.
It's showing up in more than one project, which points to a portfolio-level cause (resourcing, client dependency, or estimation) rather than one team's execution.
Sentiment and budget are excluded from this cycle's scoring where source data didn't include cost actuals or PM commentary -- flagged, not guessed.
Counts reflect the most recent scan per project.
As of 2026-07-09

## Slide 5
Spotlight: Projects Needing Attention
Red
Orion ERP Migration - Falcon Manufacturing
PM: Marcus Webb
Schedule: Red
Milestones: Red
Blockers: Amber
Sentiment: Red
Orion ERP Migration - Falcon Manufacturing is off track and needs immediate leadership intervention. Schedule: 3 of 6 active tasks (50%) are past their planned end date. 4 tasks (40%) are self-flagged Red in the plan. 3 critical-path tasks are overdue. Actual progress is running at 50% of the pace needed for the elapsed timeline. Milestones: 3 of 9 major phase(s) are past their planned end date and not yet complete (e.g. Data Migration Build, Integration Build, Security Review). Blockers: 2 dependent task(s) have a passed start date but haven't started (possible blockers). Sentiment: 3 of 6 status comments contain risk/delay language (keyword proxy, not true sentiment analysis). Note: budget could not be assessed (data not available in source file) and were excluded from the composite score.
Red
Zycus - UniSan S2P Implementation
PM: Rajat Bothra
Schedule: Red
Milestones: Red
Blockers: Red
Zycus - UniSan S2P Implementation is off track and needs immediate leadership intervention. Schedule: 44 of 234 active tasks (19%) are past their planned end date. 42 tasks (11%) are self-flagged Red in the plan. 3 critical-path tasks are overdue. Actual progress is running at 71% of the pace needed for the elapsed timeline. Milestones: 2 of 39 major phase(s) are past their planned end date and not yet complete (e.g. Training Phase I, Hypercare Phase I). Blockers: 29 dependent task(s) have a passed start date but haven't started (possible blockers). Note: budget, sentiment could not be assessed (data not available in source file) and were excluded from the composite score.
Full evidence trail available in the weekly JSON/Markdown reports per project.
As of 2026-07-09

## Slide 6
Recommendations & Next Steps
1
Address the shared bottleneck, not just the symptom
Schedule slippage is showing up across multiple projects at once -- treat it as a resourcing/estimation review, not a project-by-project fire drill.
2
Escalate stalled dependencies this week
Tasks stuck behind unmet predecessors or client-side blockers are a leading indicator of Red status; a targeted unblock call is cheaper now than a re-baseline later.
3
Close the budget and sentiment data gap
Two of five health signals could not be scored this cycle because cost actuals and PM commentary weren't captured consistently -- wiring these in sharpens every future report.
Prepared by the Professional Services Project Health Reporting Agent -- refreshed weekly.